## Cluster Triage
# | Priority | Cluster | Page Name | URL | Action | Page Type | Business Impact | Design Ref? | Dependencies | Notes
1 | P0 | AI Visibility Silo | AI Visibility Audit (Lead Magnet / CTA target) | /ai-visibility/ai-visibility-audit/ | CREATE | Money | Critical | No | — | THE most important missing page. Every CTA on the site points here. Build first.
2 | P0 | Proof | HomeCalc AI Visibility Case Study | /case-studies/homecalc-ai-visibility/ | CREATE | Proof | Critical | Yes ✓ | Real metrics from Hami | Without proof, audit page has no credibility. Need real before/after numbers.
3 | P1 | AI Visibility Silo | AEO Consultant Canada (service) | /ai-visibility/answer-engine-optimization-consultant-canada/ | CREATE | Money | High | No | Audit page exists | Service page for Answer Engine Optimization. Links to audit CTA.
4 | P1 | AI Visibility Silo | GEO Consultant Canada (service) | /ai-visibility/generative-engine-optimization-consultant-canada/ | CREATE | Money | High | No | Audit page exists | Service page for Generative Engine Optimization. Links to audit CTA.
5 | P1 | AI Visibility Silo | AI Visibility for Dental Clinics (vertical) | /ai-visibility/ai-visibility-for-dental-clinics/ | CREATE | Money | High | No | Audit page exists | Vertical-specific landing page. High local intent keyword.
6 | P1 | AI Visibility Silo | AI Visibility for Mortgage Brokers (vertical) | /ai-visibility/ai-visibility-for-mortgage-brokers/ | CREATE | Money | High | No | Audit page exists | Vertical-specific landing page. High local intent keyword.
7 | P1 | Core / Identity | Homepage | / | UPDATE | Identity | High | Yes ✓ | Audit page exists | CTA button should link to /ai-visibility/ai-visibility-audit/. Verify messaging aligns with strategy.
8 | P1 | Core / Identity | About (Entity Hub) | /hami-tahm/ | UPDATE | Identity | High | Yes ✓ | — | Add real photo. Add CTA box linking to audit. Update Person JSON-LD.
9 | P1 | AI Visibility Silo | AI Visibility Pillar (Hub) | /ai-visibility/ | UPDATE | Money | High | Yes ✓ | Child pages built | Add internal links to ALL child pages (audit, AEO, GEO, dental, mortgage, blog, case study).
10 | P1 | AI Visibility Silo | AI Visibility Consultant Canada (Cornerstone) | /ai-visibility/ai-visibility-consultant-canada/ | UPDATE | Money | High | Yes ✓ | Case study exists | Add proof links to case study. Align positioning with strategy.
11 | P2 | Blog | Blog Index | /blog/ | CREATE | Info | Medium | Yes ✓ | — | Index page listing all AI visibility blog posts. CTA strip to audit.
12 | P2 | Blog | What Is AI Visibility | /blog/what-is-ai-visibility/ | CREATE | Info | High | Yes ✓ | Blog index exists | Defines the core topic. Highest priority blog post. TL;DR box for AI extraction.
13 | P2 | Blog | AEO vs GEO vs SEO | /blog/aeo-vs-geo-vs-seo/ | CREATE | Info | High | — | Blog index exists | High search intent comparison. Supports AEO + GEO service pages.
14 | P2 | Blog | How to Get Mentioned by ChatGPT | /blog/how-to-get-mentioned-by-chatgpt/ | CREATE | Info | High | — | Blog index exists | High search intent. Direct buyer question → positions you as expert.
15 | P2 | Blog | How to Appear in Google AI Overviews | /blog/how-to-appear-in-google-ai-overviews/ | CREATE | Info | High | — | Blog index exists | High search intent. Google AIO is the biggest AI search surface.
16 | P2 | Blog | How to Get Cited by Perplexity | /blog/how-to-get-cited-by-perplexity/ | CREATE | Info | Medium | — | Blog index exists | Growing platform. Supports pillar authority.
17 | P2 | Blog | How to Check AI Visibility | /blog/how-to-check-ai-visibility/ | CREATE | Info | Medium | — | Blog index exists | Informational. Supports audit page ("or let us check for you").
18 | P2 | Blog | What Is Answer Engine Optimization | /blog/what-is-answer-engine-optimization/ | CREATE | Info | Medium | — | Blog index exists | Supports AEO service page. Defines the term.
19 | P3 | Blog (Competitive) | Best AI Visibility Tools (2025) | /blog/best-ai-visibility-tools/ | CREATE | Info | Medium | — | P2 blog posts live | Comparison listicle. Captures tool-intent traffic. End CTA: "or get an audit".
20 | P3 | Blog (Competitive) | AI Visibility Tools vs AI Visibility Audit | /blog/ai-visibility-tools-vs-audit/ | CREATE | Info | Medium | — | P2 blog posts live | Positioning piece: dashboards vs diagnosis+execution. Core differentiator.
21 | P3 | Blog (Competitive) | Peec vs Profound vs AirOps Comparison | /blog/peec-vs-profound-vs-airops/ | CREATE | Info | Medium | — | P2 blog posts live | Tool comparison. You're the expert reviewer, not a competitor. CTA to audit.
22 | P1 | Tech | JSON-LD Structured Data (all pages) | — | UPDATE | Tech | High | — | — | Add Person, ProfessionalService, FAQPage, Article schemas per STRUCTURE-AND-URLS.md spec.
23 | P1 | Tech | Internal Linking Pass | — | UPDATE | Tech | High | — | All P0+P1 pages live | Wire up all internal links per the silo linking map. Breadcrumbs on silo pages.
24 | P2 | Tech | Update sitemap.ts | — | UPDATE | Tech | Medium | — | New pages deployed | Already has future URLs listed. Remove any that 404. Add P3 blog posts when created.
25 | P2 | Tech | IndexNow API Route | /api/indexnow/ | CREATE | Tech | Low | — | — | Replaces Rankmath's IndexNow. Auto-ping Bing on deploy. Optional but speeds indexing.
26 | DONE | Core / Identity | Writing Index | /writing/ | DONE | Identity | — | Yes ✓ | — | Exists and deployed. Lists all personal posts.
27 | DONE | Core / Identity | Contact | /contact/ | DONE | Identity | — | Yes ✓ | — | Exists and deployed.
28 | DONE | Personal Posts | 31 Personal Blog Posts (WordPress migration) | Various root URLs | DONE | Content | — | — | — | All 31 posts migrated from WordPress. Flat root URLs preserved.

## Summary
Cluster Triage Summary
Total pages in plan | 28
By Action:
CREATE (new pages) | 17
UPDATE (existing pages) | 8
DONE (no changes needed) | 3
By Priority:
P0 — Critical Path (site can't convert) | 2
P1 — Money + Proof + Tech Foundation | 10
P2 — Blog + Topical Authority | 11
P3 — Competitive Content | 3
DONE — Shipped | 3
Build Order:
Sprint 1: P0 (Audit + Case Study) | ~2-3 days
Sprint 2: P1 Creates (AEO, GEO, Verticals) | ~3-4 days
Sprint 3: P1 Updates (Homepage, Pillar, JSON-LD, Links) | ~2 days
Sprint 4: P2 Blog Foundation (Index + 7 posts) | ~5-7 days
Sprint 5: P3 Competitive Content (3 posts) | ~3 days
Estimated total to complete site: | ~15-19 days

## Build Order
Execution Sequence
Order | Sprint | Page | URL | Action | Why This Order
1 | S1 | AI Visibility Audit | /ai-visibility/ai-visibility-audit/ | CREATE | CTA target — unlocks all other pages' conversion path
2 | S1 | HomeCalc Case Study | /case-studies/homecalc-ai-visibility/ | CREATE | Proof — needed before audit page can be credible
3 | S2 | AEO Consultant Canada | /ai-visibility/answer-engine-optimization-consultant-canada/ | CREATE | Service page — high-intent keyword
4 | S2 | GEO Consultant Canada | /ai-visibility/generative-engine-optimization-consultant-canada/ | CREATE | Service page — high-intent keyword
5 | S2 | AI Visibility for Dental Clinics | /ai-visibility/ai-visibility-for-dental-clinics/ | CREATE | Vertical page — specific buyer persona
6 | S2 | AI Visibility for Mortgage Brokers | /ai-visibility/ai-visibility-for-mortgage-brokers/ | CREATE | Vertical page — specific buyer persona
7 | S3 | Homepage | / | UPDATE | Point CTA to audit page now that it exists
8 | S3 | About | /hami-tahm/ | UPDATE | Add photo + audit CTA + Person schema
9 | S3 | AI Visibility Pillar | /ai-visibility/ | UPDATE | Wire links to all new child pages
10 | S3 | Consultant Canada | /ai-visibility/ai-visibility-consultant-canada/ | UPDATE | Add case study proof + strategy alignment
11 | S3 | JSON-LD Structured Data | All pages | UPDATE | Add Person, ProfessionalService, FAQPage, Article schemas
12 | S3 | Internal Linking Pass | All silo pages | UPDATE | Wire breadcrumbs + cross-links per silo map
13 | S4 | Blog Index | /blog/ | CREATE | Index page needed before blog posts
14 | S4 | What Is AI Visibility | /blog/what-is-ai-visibility/ | CREATE | Core definition post — highest priority blog
15 | S4 | AEO vs GEO vs SEO | /blog/aeo-vs-geo-vs-seo/ | CREATE | High search intent comparison
16 | S4 | How to Get Mentioned by ChatGPT | /blog/how-to-get-mentioned-by-chatgpt/ | CREATE | High buyer intent — direct question
17 | S4 | How to Appear in Google AI Overviews | /blog/how-to-appear-in-google-ai-overviews/ | CREATE | Largest AI search surface
18 | S4 | How to Get Cited by Perplexity | /blog/how-to-get-cited-by-perplexity/ | CREATE | Growing platform
19 | S4 | How to Check AI Visibility | /blog/how-to-check-ai-visibility/ | CREATE | Informational — funnels to audit
20 | S4 | What Is Answer Engine Optimization | /blog/what-is-answer-engine-optimization/ | CREATE | Supports AEO service page
21 | S5 | Best AI Visibility Tools | /blog/best-ai-visibility-tools/ | CREATE | Captures tool-intent traffic → "or get an audit"
22 | S5 | Tools vs Audit | /blog/ai-visibility-tools-vs-audit/ | CREATE | Core positioning: dashboards vs execution
23 | S5 | Peec vs Profound vs AirOps | /blog/peec-vs-profound-vs-airops/ | CREATE | Comparison post — you're the expert reviewer